## Budget Template
| Special Event: |  | Date:
Volunteer Chairman: _______________________________
Account Numbers:
Income
Expense
Expenses: |  | Current Year Budget | Current Year Actual | Last Year Actual | Comments
Facility cost
Food costs
Airline tickets
iPad
Casino Games Rental
Recognition
Awards
AV Rental Costs
Printing - Invitation
Printing S-A-D
Postage
Printing - Programs
Other:
Miscellaneous
TOTAL EXPENSES:
Special Event:
Income:
Auction:
Prize Drawings:
Additional Income:
TOTAL INCOME:
EVENT TOTAL:

## Attendance Tracking
First Name | Last Name | Date Received | Worker | Company Name | Pledge | Payment | Sponsorship Level | Address Line 1 | Address Line 2 | City | State | Zip | Email Address | Telephone | Fax | Follow Up | Notes | Invoice | Thank you

## Count Down Timeline
Event Date:
Enter Your Event Date Here
Subject | Days Before Event | Due Date
Location Secured | 110 | #VALUE!
Chairman Recruited | 360-120 | #VALUE!
Committee Letters Mailed Out | 118 | #VALUE!
Contracts Signed | 110 | #VALUE!
Event Underwriter Secured | 110 | #VALUE!
Committee Meeting #1 | 100 | #VALUE!
First Invitation Drafted - Edited by as many eyes as possible | 100 | #VALUE!
Committee Recruited | 100 | #VALUE!
Final Invitation Draft to Printer | 90 | #VALUE!
Database Finalized | 80 | #VALUE!
Invitations Mailed | 75 | #VALUE!
Committee Meeting #2 | 70 | #VALUE!
Committee Meeting #3 | 30 | #VALUE!
Program Designed | 20 | #VALUE!
PowerPoint Developed | 15 | #VALUE!
Script First Draft | 15 | #VALUE!
Committee Meeting #4 (if needed) | 10 | #VALUE!
"To Bring List" Confirmed | 7 | #VALUE!
Final Count to Hotel/Caterer | 7 | #VALUE!
Table Signs & Programs Pinted | 5 | #VALUE!
Script Final Draft Completed | 2 | #VALUE!
Table Lists | 2 | #VALUE!
Name Tags | 1 | #VALUE!
Alpha List - Registration Table (5 Copies) | 1 | #VALUE!
District Special Event | 0 | #VALUE!
Send Thank You Email to All Staff/Volunteers | -1 | #VALUE!
Send Follow-Up Letters | -7 | #VALUE!

## Day of Event Needs
Suggest Checklist for Planning an FOS Event
Make meal arrangements (-6 weeks).
Secure date and location of kick off (-6 weeks).
Mail invitations (-3 to –4 weeks).
Decorations – Flag sets.
Seating chart.
Name tags at door (prepared in advance).
Need a person to handle registration table – should not be the district executive.
Head Table.
Podium.
Script for Chair.
Introduction of speaker and head table – (script).
Script for Table Host pitch.
FOS brochures at each place setting.
District fact sheet in each brochure.
(Guest Speaker) – Let him know how long you expect him to speak.
Pledge cards divided by Table Hosts/Table Host envelopes.
Calculator – needed to announce totals.
Table Host name cards.
Blank Pledge cards.
Head Table place cards.
Table banners.
Gifts – Chair & Speaker (Chair – Commemorative Leather-bound Handbook; Pocket Knife for speaker).
Scouts for opening.
Person to give invocation.
Table Host Packet (instructions on outside)
Table Host script.
Typed pledge cards at table for all contacts (attendees clipped on outside and non-attendance on inside).
Blank pledge cards.
Envelope turn-in.

## Auction Sheet
Worker | Auction Item | Bid Increments | Min Bid | Retail Value | Buy It Now | Winning Bidder | Winning Bid | How Paid | Picked Up | Thank You To | Notes | Contact Info | Contact Info #2

## Event Cash
Day of Event Cash Accounting:
Name of Donor | Donation $ | Auction | Cash | Check | Credit Card